DONE
DONE
Hamid
Jander
WAITING
WAITING
WAITING
Raquel
DONE
DONE
Jander
WORKING
WORKING
WAITING
WAITING
WORKING
WORKING
WAITING
WAITING
Adicionar funcionalidade control z
WAITING
WORKING
desable menu options if there is no openned image
disable some menu options if there is no openned image
waITING
WAITING
WAITING
Jander
hamid
WAITING
## Environment
Programming Environment

OS	Linux
Distribution	Ubuntu 10.04
IDE	QT (qt-sdk-linux-x86-opensource-2010.05.1)

## Tasks
ID	Description	Priority	Duo Date	Status	Responsible
01	Define the content of the menu	3	04/01/11	DONE	Raquel
02	Implement Menu in QT	3	04/01/11	DONE	Jander
03	Implement Open file	3	05/01/11	DONE	Raquel
04	Implement Crop	3	08/01/11	DONE	Jander
05	Implement Pixel color information for RGB	3	08/01/11	DONE	Jander
06	Implement Color histograms	3	07/01/11	DONE	Raquel
07	Implement Color to gray scale transformation	3	08/01/11	DONE	Jander
08	Implement Blur	3	08/01/11	DONE	Hamid
09	Implement Fusion	3	08/01/11	DONE	Jander
10	Do the report document	3	26/01/11	WORKING	Hamid
11	Create base code in Qt Creator	3	04/01/11	DONE	Jander
12	Implement Quit action	3	04/01/11	DONE	Jander
13	Implement Save as	3	05/01/11	DONE	Raquel
14	Implement Save	3	06/01/11	DONE	Raquel
15	Implement Resize	3	17/01/11	DONE	Jander
16	Implement Mean Filter	3		DONE	Hamid
17	Implement Gradient Filter	3		DONE	Hamid
18	Implement Gaussian Filter	3		DONE	Hamid
19	Implement Laplacian Filter	3		DONE	Hamid
20	Implement Filter's customization	3		DONE	Hamid
21	Implement Intelligent resizing	5		WORKING	Raquel
22	Implement Intelligent scissors	5		WAITING
23	Implement Contrast and equalization	3	14/01/11	DONE	Jander
23	Merge image window and main window into a single one	2	07/01/11	DONE	Jander
24	Implement method to Generate Gaussian kernel	2	08/01/11	DONE	Hamid
24	BUG: run the application and click in the middle, it crashes	2	08/01/11	DONE	Jander
25	Implement method to apply convolution	2	08/01/11	DONE	Hamid
25	BUG: if load a large image just part of it is displayed	2	08/01/11	DONE	Jander
26	Implement method to convert RGB into YUV or CMYK	2	08/01/11	DONE	Hamid
27	Implement ImageAbstraction class (used by contrast and simplify image access)	2	07/01/11	DONE	Jander
28	Implement formats gif and pnm at save as	3		WAITING
29	Show histogram from menu, instead of at the beginning	3	11/01/11	DONE	Jander
30	Add about menu	3	28/01/11	DONE	Jander
31	Add control z feature	3	28/01/11	WORKING	Jander
32	prepare the ppt for the presentation	3	28/01/11	WAITING
33	include zoom for the image	3	28/01/11	WORKING	Hamid
34	disable some menu options if there is no opened image	3		WAITING
35	implement histogram to other image formats	3		WAITING