## Environment
Programming Environment

OS	Linux
Distribution	Ubuntu 10.04
IDE	QT (qt-sdk-linux-x86-opensource-2010.05.1)

## Tasks
ID	Description	Priority	Duo Date	Status	Responsible
24	Implement method to Generate Gaussian kernel	2	08/01/11	WAITING	Hamid
25	Implement method to apply convolution	2	08/01/11	WAITING	Hamid
26	Implement method to convert RGB into YUV or CMYK	2	08/01/11	WAITING	Hamid
27	Implement ImageAbstraction class (used by contrast and simplify image access)	2	07/01/11	WAITING	Jander
01	Define the content of the menu	3	04/01/11	DONE	Raquel
02	Implement Menu in QT	3	04/01/11	DONE	Jander
03	Implement Open file	3	05/01/11	DONE	Raquel
04	Implement Crop	3	08/01/11	WAITING
05	Implement Pixel color information for RGB	3	08/01/11	WORKING	Jander
06	Implement Color histograms	3	08/01/11	WAITING
07	Implement Color to gray scale transformation	3	08/01/11	WAITING
08	Implement Blur	3	08/01/11	WAITING
09	Implement Fusion	3	08/01/11	WAITING
10	Do the report document	3	26/01/11	WAITING
11	Create base code in Qt Creator	3	04/01/11	DONE	Jander
12	Implement Quit action	3	04/01/11	DONE	Jander
13	Implement Save as	3	05/01/11	DONE	Raquel
14	Implement Save	3	06/01/11	WORKING	Raquel
15	Implement Resize	3		WAITING
16	Implement Mean Filter	3		WAITING
17	Implement Gradient Filter	3		WAITING
18	Implement Gaussian Filter	3		WAITING
19	Implement Laplacian Filter	3		WAITING
20	Implement Filter's customization	3		WAITING
23	Implement Contrast and equalization	3		WAITING
28		3
29		3
30		3
31		3
32		3
33		3
34		3
35		3
36		3
37		3
21	Implement Intelligent resizing	5		WAITING
22	Implement Intelligent scissors	5		WAITING