DONE
DONE
Hamid
Jander
WAITING
WAITING
WAITING
Raquel
DONE
DONE
Jander
WORKING
WORKING
WAITING
WAITING
WORKING
WORKING
WAITING
WAITING
Adicionar funcionalidade control z
WAITING
WORKING
desable menu options if there is no openned image
disable some menu options if there is no openned image
waITING
WAITING
WAITING
Jander
hamid
WAITING
Hamid
WORKING
WAITING
WORKING
WORKING
## Environment
Programming Environment

OS	Linux
Distribution	Ubuntu 10.04
IDE	QT (qt-sdk-linux-x86-opensource-2010.05.1)

## Tasks
ID	Description	Priority	Duo Date	Status	Responsible
01	Define the content of the menu	3	04/01/11	DONE	Raquel
02	Implement Menu in QT	3	04/01/11	DONE	Jander
03	Implement Open file	3	05/01/11	DONE	Raquel
04	Implement Crop	3	08/01/11	DONE	Jander
05	Implement Pixel color information for RGB	3	08/01/11	DONE	Jander
06	Implement Color histograms	3	07/01/11	DONE	Raquel
07	Implement Color to gray scale transformation	3	08/01/11	DONE	Jander
08	Implement Blur	3	08/01/11	DONE	Hamid
09	Implement Fusion	3	08/01/11	DONE	Jander
10	Do the report document	3	26/01/11	WORKING	Hamid
11	Create base code in Qt Creator	3	04/01/11	DONE	Jander
12	Implement Quit action	3	04/01/11	DONE	Jander
13	Implement Save as	3	05/01/11	DONE	Raquel
14	Implement Save	3	06/01/11	DONE	Raquel
15	Implement Resize	3	17/01/11	DONE	Jander
16	Implement Mean Filter	3		DONE	Hamid
17	Implement Gradient Filter	3		DONE	Hamid
18	Implement Gaussian Filter	3		DONE	Hamid
19	Implement Laplacian Filter	3		DONE	Hamid
20	Implement Filter's customization	3		DONE	Hamid
21	Implement Intelligent resizing	5		DONE	Raquel
22	Implement Intelligent scissors	5		WAITING
23	Implement Contrast and equalization	3	14/01/11	DONE	Jander
23	Merge image window and main window into a single one	2	07/01/11	DONE	Jander
24	Implement method to Generate Gaussian kernel	2	08/01/11	DONE	Hamid
24	BUG: run the application and click in the middle, it crashes	2	08/01/11	DONE	Jander
25	Implement method to apply convolution	2	08/01/11	DONE	Hamid
25	BUG: if load a large image just part of it is displayed	2	08/01/11	DONE	Jander
26	Implement method to convert RGB into YUV or CMYK	2	08/01/11	DONE	Hamid
27	Implement ImageAbstraction class (used by contrast and simplify image access)	2	07/01/11	DONE	Jander
28	Implement formats gif and pnm at save as	3		WAITING
29	Show histogram from menu, instead of at the beginning	3	11/01/11	DONE	Jander
30	Add about menu	3	28/01/11	DONE	Jander
31	Add control z feature	3	28/01/11	DONE	Jander
32	prepare the ppt for the presentation	3	28/01/11	WAITING
33	include zoom for the image	3	28/01/11	DONE	Jander
34	disable some menu options if there is no opened image	3		DONE	Jander
35	implement histogram to other image formats	3		WAITING