## Environment
Programming Environment

OS	Linux
Distribution	Ubuntu 10.04
IDE	QT (qt-sdk-linux-x86-opensource-2010.05.1)

## Tasks
ID	Description	Duo Date	Status	Responsible
01	Spec Menu (define the content of the menu)	04/01/11	DONE	Raquel
02	Implement Menu in QT	04/01/11	DONE	Jander
03	Reading and Writing images library		WAITING
04	Implement Crop		WAITING
05	Pixel color information		WAITING
06	Color histograms		WAITING
07	Color to gray scale transformation		WAITING
08	Blur		WAITING
09	Fusion		WAITING
10	Do the report document	26/01/11	WAITING
11	Create base code in Qt Creator	04/01/11	DONE	Jander
12	Implement Quit action	04/01/11	WORKING	Jander